## README
JOBCOST — 2026001 Rockland (MOCK, pilot-scale demo)
NOT the canonical template | This file is a lightweight pilot-scale mock for Drive-organization and parser-shape demonstration only. The canonical, owner-built gold-standard JOBCOST workbook is docs/JOB_COST_TEMPLATE_structured.xlsx (Project_Setup, Cost_Ledger, Scope_Budget, Change_Orders, Order_Quantities, Cost_Code_Summary, Progress_Valuation, Dashboard, Lists, Parser_Contract).
Production rule | For each real project, copy JOB_COST_TEMPLATE_structured.xlsx into the project folder as {project_code}_JOBCOST.xlsx and use ITS Parser_Contract as the ingestion contract. Do not build a separate simplified JOBCOST model.
Purpose of this mock | Demonstrate the same sheet roles at smaller scale: actuals (Cost_Ledger) + forecast (Scope_Budget) + change orders + order quantities.
Main input tables | tblCostLedger, tblScopeBudget, tblChangeOrders, tblOrderQuantities.
Append rule | Append rows inside named tables. Do not build summaries from fixed row ranges.
Parser rule | Only ingest sheets listed Ingest=Y in Parser_Contract.

## Project_Setup
Code | Value | Units | Description
Project_Name | 2026001 — Rockland | text | Project display name
Project_Code | 2026001 | text | Canonical 7-digit project code
Legacy_Job_Number | 923 | text | Previous short reference
Tax_Rate | 0.15 | rate | QC: TPS+TVQ combined
Global_Markup_Rate | 0.15 | rate | Applied to inflated subtotal -> client price
Total_Units | 1 | units | Rockland pilot = 1 unit (single renovation)

## Cost_Ledger
Entry_ID | Date | Source | Cost_Type | Cost_Class | Trade | Cost_Code | Scope_Area | Item_Description | Supplier_Subcontractor | SOW_Item_Ref | Manual_Amount_Incl_Tax | Tax_Included | Tax_Rate | Amount_Incl_Tax | Amount_Excl_Tax | Include_In_Actual | Include_In_Budget | Notes
MAT-0001 | 2026-07-05 | Invoice | Actual | Material | Finishes | 09 | Unit 923 | LVP Flooring (Lifeproof 6mm) | Home Depot | SOW-021 | 1850 | Yes | 0.15 | 1850 | 1608.7 | Yes | No | Receipt on file
LAB-0001 | 2026-07-10 | Invoice | Actual | Subcontractor | Plumbing | 22 | Unit 923 | Rough-in plumbing | Plombert Inc. | SOW-025 | 3200 | Yes | 0.15 | 3200 | 2782.61 | Yes | No | PO 2026001-001
MAT-0002 |  | Committed | Committed | Material | Finishes | 09 | Unit 923 | Porcelain tile 12x24 | Mondial | SOW-019 | 2400 | Yes | 0.15 | 2400 | 2086.96 | No | Yes | Order pending

## Scope_Budget
Line_ID | Line_Role | Source_Type | Cost_Class | Trade | Cost_Code | Scope_Area | Item | Unit_Price | Quantity_Per_Affected_Unit | Affected_Units | Tax_Included | Tax_Rate | Amount_Incl_Tax | Amount_Excl_Tax | Include_Current_Forecast | Include_Quote_Total | Include_Target_Budget | Notes
BUD-0001 | Quote_Total | Quote | Subcontractor | Plumbing | 22 | Unit 923 | Plumbing (Plombert Inc. selected quote) | 6800 | 1 | 1 | Yes | 0.15 | 7820 | 6800 | Yes | Yes | Yes | Source: 2026001_QUOTE_22-Plumbing_PlombertInc_selected.xlsx
BUD-0002 | Allowance | Current_Forecast | Material | Finishes | 09 | Unit 923 | Tile allowance (12x24 porcelain) | 3500 | 1 | 1 | Yes | 0.15 | 4025 | 3500 | Yes | No | Yes | Client-selected, pending invoice
BUD-0003 | Quote_Total | Quote | Subcontractor | Finishes | 09 | Unit 923 | Finishes (ABC Tile pending quote) | 21500 | 1 | 1 | Yes | 0.15 | 24725 | 21500 | Yes | Yes | Yes | Source: 2026001_QUOTE_09-Finishes_ABCTile_pending.xlsx

## Change_Orders
CO_ID | Item | Description | Cost_Before_OHP | OHP_Rate | Total_With_OHP | Status | Billable | Reason | SOW_Item_Ref
CO-001 | Extra demo | Additional demo for hidden rot in subfloor | 800 | 0.15 | 920 | Pending | Yes | Unforeseen condition

## Order_Quantities
Order_ID | Cost_Class | Cost_Code | Item | Qty_Per_Pack | Number_Of_Packs | Total_Units | Order_Status | Supplier | Notes
ORD-0001 | Material | 09 | Porcelain tile 12x24 (box/10 sqft) | 10 | 28 | 280 | Open | Mondial | Bathroom + hallway
ORD-0002 | Material | 09 | LVP flooring (box/20 sqft) | 20 | 18 | 360 | Ordered | Home Depot | Living + bedroom
ORD-0003 | Material | 22 | PEX-A 1/2" (roll/100ft) | 100 | 2 | 200 | Ordered | Home Depot

## Lists
Cost_Class | Cost_Type | Order_Status | CO_Status | Quote_Status
Material | Actual | Open | Pending | pending
Labour | Committed | Ordered | Paid | recommended
Subcontractor | Forecast | Received | Not Executed | selected
Equipment | Quote | Cancelled | Cancelled | rejected
awarded

## Parser_Contract
Sheet_Name | Ingest | Table_Name | Primary_Key | Notes
README | N | — | — | Human instructions — do not ingest
Project_Setup | Y | tblProjectSettings | Code | Controlled project variables. Read by Code field.
Cost_Ledger | Y | tblCostLedger | Entry_ID | Canonical actuals. Include_In_Actual=Yes -> actuals; Include_In_Budget=Yes -> budget.
Scope_Budget | Y | tblScopeBudget | Line_ID | Allowances, quote totals, manual overrides. Inclusion flags control forecast/quote/budget.
Change_Orders | Y | tblChangeOrders | CO_ID | Change orders. Status=Paid rows count toward actuals.
Order_Quantities | Y | tblOrderQuantities | Order_ID | Materials on order. Order_Status tracks receipt.
Lists | N | — | — | Dropdown validation — do not ingest
Parser_Contract | N | — | — | Parser instructions (this sheet)