## README
JOB COST TEMPLATE — structured replacement workbook
Purpose | This workbook replaces the old layout-driven job-costing file with table-driven inputs and formulas.
Core rule | Append and sort inside Excel Tables. Do not build summaries from fixed row ranges like C6:C69.
Main input tables | tblCostLedger, tblScopeBudget, tblChangeOrders, tblOrderQuantities, tblProjectSettings.
Summary logic | Dashboard and Cost_Code_Summary use SUMIFS by Cost_Class, Cost_Code, flags, and settings.
Generalizable units | Change Project_Setup → Total_Units. Per-unit allowances and quotes multiply by affected units.
Material actuals | Material and supplier purchases belong in Cost_Ledger with Cost_Class = Material.
Labour actuals | Labour/subcontractor actuals belong in Cost_Ledger with Cost_Class = Labour or Subcontractor.
Allowances/quotes | Per-unit constants like cabinets, counters, quoted labour, and quoted material belong in Scope_Budget.
Change orders | Use Billable and Include_In_Progress flags; do not rely on the Status text alone.
Known imported anomaly | Original Material!J36 labelled Doors but summed C6:C69. This template does not reproduce that bug; Doors now means rows tagged Doors.
Clearing for reuse | To make a blank template, clear data rows in Cost_Ledger, Scope_Budget, Change_Orders, and Order_Quantities, but leave headers/formula columns/settings.
Imported CO5 normalization | Original CO5 had Cost/Unit × Applied Units not matching Total. The structured template normalizes Cost_Per_Unit so the formula-driven total equals the original $5,240.00; review before using that specific row as precedent.

## Project_Setup
Project Setup / Controlled Variables
Code | Value | Units | Description | Original Source / Note | Derived Metric | Formula / Value | Meaning
Project_Name | Imported Job Costing Template | text | Project name displayed on summaries. | New controlled input | Quote_Per_Unit_From_Initial_Quote | 7800 | Initial_Quote_Total / Initial_Quoted_Units
Total_Units | 15 | units | Total project units. Most per-unit allowances multiply by this. | Original workbook used 15 repeatedly. | Quote_Total_For_All_Units | 117000 | Quote per unit scaled to Total_Units
Initial_Quoted_Units | 10 | units | Units in original Jair quote. | Material!H11:I13 | Receivable_Total | 322500 | Receivable_Per_Unit × Total_Units
Initial_Quote_Total | 78000 | currency | Original quote for Initial_Quoted_Units. | Material!I11 | Target_Spend_Per_Unit | 17200 | Receivable_Per_Unit × (1 - Target_Profit_Rate)
Receivable_Per_Unit | 21500 | currency/unit | Expected receivable per completed unit. | Material!I15 | Target_Spend_Total | 258000 | Target_Spend_Per_Unit × Total_Units
Base_Price_Per_Unit_PreTax | 20580 | currency/unit | Base original price used by progress valuation. | Value of Progress!C3/I15 | Base_Contract_Total_After_Tax | 355005 | Base_Price_Per_Unit_PreTax × Total_Units × (1 + Tax_Rate)
Material_Budget_Per_Unit | 9200 | currency/unit | Target material budget per unit. | Material!I4
Labour_Budget_Per_Unit | 8000 | currency/unit | Target labour budget per unit. | Material!P4
Target_Profit_Rate | 20% | percent | Target profit percentage. | Original target spend used 20%.
Tax_Rate | 15% | percent | Tax rate used to convert tax-included costs. | Original divided by 1.15.
OHP_Rate | 15% | percent | Overhead/profit rate for change orders. | EXTRAS!G18
Current_Payments_To_Date | 137969 | currency | Payments received to date for progress valuation. | Value of Progress!C2
Manual_Value_Adjustment | 4000 | currency | Adjustment used in original progress actual value formula. | Value of Progress!H19

## Dashboard
Job Cost Dashboard
Metric | Current Formula Result | Original Equivalent / Meaning | Rule | KPI | Value | Status
Total Units | 15 | 15 units | Controlled input from Project_Setup | Material over/under per unit | -2951.5333 | Over budget
Material Budget / Unit | 9200 | $9,200.00 | Project_Setup variable | Labour over/under per unit | 2218.104 | Within budget
Actual Material Ledger / Unit | 6901.5333 | $6,901.53 old I9 | SUMIFS Cost_Ledger where Cost_Class=Material and Include_In_Actual=Yes | Current cost vs target / unit | 1605.7136 | Under target
Current Material Forecast Addons / Unit | 5250 | $5,250.00 old I5+I6+I7 | SUMIFS Scope_Budget where Cost_Class=Material and Include_Current_Forecast=Yes
Current Material Forecast / Unit | 12151.5333 | $12,151.53 old J4 | Actual material per unit + addons per unit
Material Variance / Unit | -2951.5333 | -$2,951.53 old K4 | Budget - forecast
Labour Budget / Unit | 8000 | $8,000.00 | Project_Setup variable
Actual Labour Ledger / Unit | 5781.896 | $5,781.90 old T11 | SUMIFS Cost_Ledger where Cost_Class=Labour and Include_In_Actual=Yes
Labour Variance / Unit | 2218.104 | Old Q4 used $9,000, but actual labour table implies $5,781.90/unit | Budget - actual labour per unit
Receivable / Unit | 21500 | $21,500.00 old I15 | Project_Setup variable
Receivable Total | 322500 | $322,500.00 old I16 | Receivable / Unit × Total Units
Target Spend / Unit | 17200 | $17,200.00 old I17 | Receivable / Unit × (1 - Target Profit Rate)
Target Spend Total | 258000 | $258,000.00 old I18 | Target Spend / Unit × Total Units
Current Cost / Unit Excl Tax | 15594.2864 | $15,594.29 old I20 | Actual + forecast addons, tax-normalized, divided by units
Quoted Labour / Unit | 7800 | $7,800.00 old S36/I13 | SUMIFS Scope_Budget quote labour / Total Units
Quoted Labour Total | 117000 | $117,000.00 old I12/T30:T33 | Quote labour for all units
Quoted Material Total | 20593.73 | $20,593.73 old S53 | Manual quote override line in Scope_Budget
Billable Extras Before OHP | 28487.98 | $28,487.98 old EXTRAS!G17 | SUMIFS Change_Orders Billable=Yes
Billable Extras With OHP | 32761.177 | $32,761.18 old EXTRAS!G18 | SUMIFS Change_Orders Billable=Yes with OHP rate
Order Quantity Total Units | 683 | 683 | SUM tblOrderQuantities[Total_Units]

## Cost_Ledger
Cost Ledger — actual costs and committed costs
Every purchase, labour cost, subcontractor invoice, refund, or committed cost goes here. Summary sheets only read this table through Cost_Class, Cost_Code, and Include flags.
Entry_ID | Date | Source | Cost_Type | Cost_Class | Trade | Cost_Code | Scope_Area | Item_Description | Supplier_Subcontractor | Units_Affected | Quantity | Unit_Cost | Manual_Amount_Incl_Tax | Tax_Included | Tax_Rate | Amount_Incl_Tax | Amount_Excl_Tax | Include_In_Actual | Include_In_Budget | Notes | Original_Phase
MAT-0001 | in progress | Original Material | Actual | Material | Finishing | Finishing | All Units | Floor | Ecarpet | 15 |  |  | 11506.24 | Yes | 15% | 11506.24 | 10005.4261 | Yes | No | flooring ¦ Imported from Material!A6:F6 | Finishing
MAT-0002 |  | Original Material | Actual | Material | Finishing | Finishing | All Units | Tile | Mondial | 15 |  |  | 11361.82 | Yes | 15% | 11361.82 | 9879.8435 | Yes | No | tiles ¦ Imported from Material!A7:F7 | Finishing
MAT-0003 |  | Original Material | Actual | Material | Finishing | Finishing | All Units | Grout | Mondial | 15 |  |  | 1109.1 | Yes | 15% | 1109.1 | 964.4348 | Yes | No | grout ¦ Imported from Material!A8:F8 | Finishing
MAT-0004 | 2026-02-11 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 8221.08 | Yes | 15% | 8221.08 | 7148.7652 | Yes | No | Imported from Material!A9:F9 | Rough
MAT-0005 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 1204.46 | Yes | 15% | 1204.46 | 1047.3565 | Yes | No | Imported from Material!A10:F10 | Rough
MAT-0006 | 2026-02-20 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 752.08 | Yes | 15% | 752.08 | 653.9826 | Yes | No | erik refunded arya personally ¦ Imported from Material!A11:F11 | Rough
MAT-0007 | 2026-02-18 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 92.37 | Yes | 15% | 92.37 | 80.3217 | Yes | No | Imported from Material!A12:F12 | Rough
MAT-0008 | 2026-02-18 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 34.43 | Yes | 15% | 34.43 | 29.9391 | Yes | No | Imported from Material!A13:F13 | Rough
MAT-0009 | 2026-02-18 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 91.79 | Yes | 15% | 91.79 | 79.8174 | Yes | No | Imported from Material!A14:F14 | Rough
MAT-0010 | 2026-02-20 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 157.7 | Yes | 15% | 157.7 | 137.1304 | Yes | No | refunded, not refunded on company** ¦ Imported from Material!A15:F15 | Rough
MAT-0011 | 2026-02-20 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 762.52 | Yes | 15% | 762.52 | 663.0609 | Yes | No | Imported from Material!A16:F16 | Rough
MAT-0012 | 2026-02-18 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 1778.54 | Yes | 15% | 1778.54 | 1546.5565 | Yes | No | Imported from Material!A17:F17 | Rough
MAT-0013 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 4015.73 | Yes | 15% | 4015.73 | 3491.9391 | Yes | No | Imported from Material!A18:F18 | Rough
MAT-0014 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 164.87 | Yes | 15% | 164.87 | 143.3652 | Yes | No | Imported from Material!A19:F19 | Rough
MAT-0015 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 195.16 | Yes | 15% | 195.16 | 169.7043 | Yes | No | Imported from Material!A20:F20 | Rough
MAT-0016 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 169 | Yes | 15% | 169 | 146.9565 | Yes | No | Imported from Material!A21:F21 | Rough
MAT-0017 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 499.74 | Yes | 15% | 499.74 | 434.5565 | Yes | No | paid by jair ¦ Imported from Material!A22:F22 | Rough
MAT-0018 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 3316.28 | Yes | 15% | 3316.28 | 2883.7217 | Yes | No | Imported from Material!A23:F23 | Rough
MAT-0019 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 644.55 | Yes | 15% | 644.55 | 560.4783 | Yes | No | 1913.98-1269.43 refund = ¦ Imported from Material!A24:F24 | Rough
MAT-0020 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 30.5 | Yes | 15% | 30.5 | 26.5217 | Yes | No | Imported from Material!A25:F25 | Rough
MAT-0021 | 2026-03-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 3408.78 | Yes | 15% | 3408.78 | 2964.1565 | Yes | No | paint, valves, level quick, other ¦ Imported from Material!A26:F26 | Rough
MAT-0022 | 2026-03-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 32.99 | Yes | 15% | 32.99 | 28.687 | Yes | No | truck rental gas ¦ Imported from Material!A27:F27 | Rough
MAT-0023 | 2026-03-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 60.73 | Yes | 15% | 60.73 | 52.8087 | Yes | No | truck rental ¦ Imported from Material!A28:F28 | Rough
MAT-0024 | 2026-03-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | -320.56 | Yes | 15% | -320.56 | -278.7478 | Yes | No | refund for 4'' piping ¦ Imported from Material!A29:F29 | Rough
MAT-0025 | 2026-03-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | -722.43 | Yes | 15% | -722.43 | -628.2 | Yes | No | refund for 4'' piping ¦ Imported from Material!A30:F30 | Rough
MAT-0026 | 2026-03-13 | Original Material | Actual | Material | Finishing | Finishing | All Units | baseboards/moldings | lefebrve | 15 |  |  | 1232.62 | Yes | 15% | 1232.62 | 1071.8435 | Yes | No | Imported from Material!A31:F31 | Finish
MAT-0027 | 2026-03-13 | Original Material | Actual | Material | Doors | Doors | All Units | Misc | lefebrve | 15 |  |  | 688.55 | Yes | 15% | 688.55 | 598.7391 | Yes | No | 18 handles and ¦ Imported from Material!A32:F32 | Doors
MAT-0028 | 2026-03-13 | Original Material | Actual | Material | Doors | Doors | All Units | Misc | lefebrve | 15 |  |  | 86.23 | Yes | 15% | 86.23 | 74.9826 | Yes | No | shipping ¦ Imported from Material!A33:F33 | Doors
MAT-0029 |  | Original Material | Actual | Material | OHP | OHP | All Units | Misc | arya | 15 |  |  | 2070 | Yes | 15% | 2070 | 1800 | Yes | No | Imported from Material!A34:F34 | ohp
MAT-0030 | 2026-03-18 | Original Material | Actual | Material | Finishing | Finishing | All Units | Lights, plates, thermostats | Amazon | 15 |  |  | 3100 | Yes | 15% | 3100 | 2695.6522 | Yes | No | Imported from Material!A35:F35 | Finishing
MAT-0031 | 2026-03-19 | Original Material | Actual | Material | Plumbing | Bathroom/Plumbing | All Units | Misc | U-Haul | 15 |  |  | 234 | Yes | 15% | 234 | 203.4783 | Yes | No | truck ¦ Imported from Material!A36:F36 | Bathroom
MAT-0032 | 2026-03-22 | Original Material | Actual | Material | Finishing | Finishing | All Units | Baseboard Heaters | Rona | 15 |  |  | 3334.81 | Yes | 15% | 3334.81 | 2899.8348 | Yes | No | Imported from Material!A37:F37 | Finishing
MAT-0033 |  | Original Material | Actual | Material | Finishing | Finishing | All Units | Plates. thermostats | Amazon | 15 |  |  | 582.91 | Yes | 15% | 582.91 | 506.8783 | Yes | No | Imported from Material!A38:F38 | Finishing
MAT-0034 | 2026-03-18 | Original Material | Actual | Material | Rough | Rough | All Units | Floor Leveling | Home depot | 15 |  |  | 1411.74 | Yes | 15% | 1411.74 | 1227.6 | Yes | No | 35 bags of level quick ¦ Imported from Material!A43:F43 | Rough
MAT-0035 | 2026-03-20 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Plumbing | Home depot | 15 |  |  | 185.84 | Yes | 15% | 185.84 | 161.6 | Yes | No | plumbing stuff ¦ Imported from Material!A44:F44 | Rough
MAT-0036 | 2026-03-21 | Original Material | Actual | Material | Rough | Rough | All Units |  | Home depot | 15 |  |  | -103.26 | Yes | 15% | -103.26 | -89.7913 | Yes | No | return of 7/8'' valve connections ¦ Imported from Material!A45:F45 | Rough
MAT-0037 | 2026-03-21 | Original Material | Actual | Material | Rough | Rough | All Units |  | Home depot | 15 |  |  | 64.69 | Yes | 15% | 64.69 | 56.2522 | Yes | No | 1/2'' valve connections ¦ Imported from Material!A46:F46 | Rough
MAT-0038 | 2026-03-24 | Original Material | Actual | Material | Rough | Rough | All Units |  | Home depot | 15 |  |  | 222.7 | Yes | 15% | 222.7 | 193.6522 | Yes | No | cement, grout, garbage bags ¦ Imported from Material!A47:F47 | Rough
MAT-0039 | 2026-03-25 | Original Material | Actual | Material | Finishing | Finishing | All Units | Paint | RONA | 15 |  |  | 848.48 | Yes | 15% | 848.48 | 737.8087 | Yes | No | paint ¦ Imported from Material!A48:F48 | Finishing
MAT-0040 | 2026-03-25 | Original Material | Actual | Material | Finishing | Finishing | All Units | Lights | Amazon | 15 |  |  | 1223.72 | Yes | 15% | 1223.72 | 1064.1043 | Yes | No | Lights, bathroom hardware ¦ Imported from Material!A49:F49 | Finishing
MAT-0041 | 2026-03-27 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Plumbing | Home depot | 15 |  |  | 344.14 | Yes | 15% | 344.14 | 299.2522 | Yes | No | plumbing stuff ¦ Imported from Material!A50:F50 | Bathroom
MAT-0042 | 2026-03-29 | Original Material | Actual | Material | Finishing | Finishing | All Units | Closet Racks | RONA | 15 |  |  | 237.36 | Yes | 15% | 237.36 | 206.4 | Yes | No | Closet racks ¦ Imported from Material!A51:F51 | Finishing
MAT-0043 | 2026-03-30 | Original Material | Actual | Material | Finishing | Finishing | All Units | Coat Hooks | Amazon | 15 |  |  | 361.9 | Yes | 15% | 361.9 | 314.6957 | Yes | No | coat hooks ¦ Imported from Material!A52:F52 | Finishing
MAT-0044 | 2026-03-31 | Original Material | Actual | Material | Finishing | Finishing | All Units | Tile Trims | Amazon | 15 |  |  | 181.3 | Yes | 15% | 181.3 | 157.6522 | Yes | No | Metal transition trims ¦ Imported from Material!A53:F53 | Finishing
MAT-0045 | 2026-04-01 | Original Material | Actual | Material | Plumbing | Bathroom/Plumbing | All Units | Shower kits | Plomberie Royalmount | 15 |  |  | 718.6 | Yes | 15% | 718.6 | 624.8696 | Yes | No | 3 shower heads + 1 corner base ¦ Imported from Material!A54:F54 | Bathroom
MAT-0046 | 2026-04-05 | Original Material | Actual | Material | Finishing | Finishing | All Units | Door stops | Amazon | 15 |  |  | 409.09 | Yes | 15% | 409.09 | 355.7304 | Yes | No | Door stoppers and Fan vents ¦ Imported from Material!A55:F55 | Finishing
MAT-0047 | 2026-04-08 | Original Material | Actual | Material | Rough | Rough | All Units | Framing wood | Home depot | 15 |  |  | 486.46 | Yes | 15% | 486.46 | 423.0087 | Yes | No | Wood studs and forrense ¦ Imported from Material!A56:F56 | Rough
MAT-0048 | 2026-04-08 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Plumbing | Home depot | 15 |  |  | 486.36 | Yes | 15% | 486.36 | 422.9217 | Yes | No | plumbing ¦ Imported from Material!A57:F57 | Bathroom
MAT-0049 | 2026-04-08 | Original Material | Actual | Material | Rough | Rough | All Units | Self Level, Drywall, Screws | Home depot | 15 |  |  | 3245.21 | Yes | 15% | 3245.21 | 2821.9217 | Yes | No | For next units: self leveling, drywall, compound, screws ¦ Imported from Material!A58:F58 | Rough
MAT-0050 | 2026-04-08 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 75.84 | Yes | 15% | 75.84 | 65.9478 | Yes | No | Imported from Material!A59:F59 | Rough
MAT-0051 | 2026-04-08 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Plumbing | Home depot | 15 |  |  | 402.04 | Yes | 15% | 402.04 | 349.6 | Yes | No | Additional plumbing ¦ Imported from Material!A60:F60 | Bathroom
MAT-0052 | 2026-04-09 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 79.54 | Yes | 15% | 79.54 | 69.1652 | Yes | No | Imported from Material!A61:F61 | Rough
MAT-0053 | 2026-04-10 | Original Material | Actual | Material | Electrical | Electrical | All Units | Rough | Home depot | 15 |  |  | 145 | Yes | 15% | 145 | 126.087 | Yes | No | Additional electrical ¦ Imported from Material!A62:F62 | Electrical
MAT-0054 | 2026-04-10 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | -106 | Yes | 15% | -106 | -92.1739 | Yes | No | Imported from Material!A63:F63 | Rough
MAT-0055 | 2026-04-10 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | -69 | Yes | 15% | -69 | -60 | Yes | No | Imported from Material!A64:F64 | Rough
MAT-0056 | 2026-04-20 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 16 | Yes | 15% | 16 | 13.913 | Yes | No | Imported from Material!A65:F65 | Rough
MAT-0057 | 2026-04-20 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Plumbing | Home depot | 15 |  |  | 635.5 | Yes | 15% | 635.5 | 552.6087 | Yes | No | Additional plumbing ¦ Imported from Material!A66:F66 | Bathroom
MAT-0058 |  | Original Material | Actual | Material | Finishing | Finishing | All Units | Blinds | Sami | 15 |  |  | 4445 | Yes | 15% | 4445 | 3865.2174 | Yes | No | Blinds ¦ Imported from Material!A67:F67 | Finishing
MAT-0059 |  | Original Material | Actual | Material | Doors | Doors | All Units | Doors (+ Labour) |  | 15 |  |  | 13455 | Yes | 15% | 13455 | 11700 | Yes | No | Doors (to be cut) ¦ Imported from Material!A68:F68 | Doors
MAT-0060 |  | Original Material | Actual | Material | Rough | Rough | All Units | Misc | ?????? | 15 |  |  | 3000 | Yes | 15% | 3000 | 2608.6957 | Yes | No | material ¦ Imported from Material!A69:F69 | Rough
MAT-0061 | 2026-04-22 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Pex | Home Depot | 15 |  |  | 92.9 | Yes | 15% | 92.9 | 80.7826 | Yes | No | Imported from Material!A70:F70 | Plumbing
MAT-0062 | 2026-04-24 | Original Material | Actual | Material | Finishing | Finishing | All Units | Paint | Home Depot | 15 |  |  | 244.9 | Yes | 15% | 244.9 | 212.9565 | Yes | No | Imported from Material!A71:F71 | Finishing
MAT-0063 | 2026-04-27 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home Depot | 15 |  |  | 180.02 | Yes | 15% | 180.02 | 156.5391 | Yes | No | Imported from Material!A72:F72 | Rough
MAT-0064 | 2026-04-27 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Valves | Home Depot | 15 |  |  | 216.01 | Yes | 15% | 216.01 | 187.8348 | Yes | No | Imported from Material!A73:F73 | Plumbing
MAT-0065 | 2026-05-05 | Original Material | Actual | Material | Finishing | Finishing | All Units | Mortar for tile | Home depot | 15 |  |  | 385.44 | Yes | 15% | 385.44 | 335.1652 | Yes | No | Imported from Material!A74:F74 | Finishing
MAT-0066 | 2026-05-06 | Original Material | Actual | Material | HVAC | HVAC | All Units | Ducts |  | 15 |  |  | 393.78 | Yes | 15% | 393.78 | 342.4174 | Yes | No | HVAC supplies ¦ Imported from Material!A75:F75 | HVAC
MAT-0067 | 2026-05-13 | Original Material | Actual | Material | Rough | Rough | All Units | Misc | Home depot | 15 |  |  | 691.46 | Yes | 15% | 691.46 | 601.2696 | Yes | No | paint, end caps (plumbing) ¦ Imported from Material!A76:F76 | Rough
MAT-0068 | 2026-05-15 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Extra - Hot water sollution | Home depot | 15 |  |  | 179.98 | Yes | 15% | 179.98 | 156.5043 | Yes | No | Imported from Material!A77:F77 | Plumbing
MAT-0069 | 2026-05-19 | Original Material | Actual | Material | Electrical | Electrical | All Units | Breakers | Home depot | 15 |  |  | 456.41 | Yes | 15% | 456.41 | 396.8783 | Yes | No | Imported from Material!A78:F78 | Electrical
MAT-0070 | 2026-05-19 | Original Material | Actual | Material | Finishing | Finishing | All Units | Misc | RONA | 15 |  |  | 258.38 | Yes | 15% | 258.38 | 224.6783 | Yes | No | Closet racks ¦ Imported from Material!A79:F79 | Finishing
MAT-0071 | 2026-05-19 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | Amazon | 15 |  |  | 35.46 | Yes | 15% | 35.46 | 30.8348 | Yes | No | Plastic envelopes for deficiencies ¦ Imported from Material!A80:F80 | General conditions
MAT-0072 | 2026-05-19 | Original Material | Actual | Material | Finishing | Finishing | All Units | Misc | Amazon | 15 |  |  | 114.96 | Yes | 15% | 114.96 | 99.9652 | Yes | No | Door stoppers ¦ Imported from Material!A81:F81 | Finishing
MAT-0073 | 2026-05-25 | Original Material | Actual | Material | Finishing | Finishing | All Units | Misc | Amazon | 15 |  |  | 91.96 | Yes | 15% | 91.96 | 79.9652 | Yes | No | Blank wall plates ¦ Imported from Material!A82:F82 | Finishing
MAT-0074 | 2026-05-26 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Kitchen sinks | RONA | 15 |  |  | 1983.32 | Yes | 15% | 1983.32 | 1724.6261 | Yes | No | Kitchen sinks ¦ Imported from Material!A83:F83 | Plumbing
MAT-0075 |  | Original Material | Actual | Material | Finishing | Finishing | All Units | Additional Floors | Ecarpet | 15 |  |  | 635.49 | Yes | 15% | 635.49 | 552.6 | Yes | No | Imported from Material!A84:F84 | Finishing
MAT-0076 | 2026-05-27 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | P-Traps and tubes |  | 15 |  |  | 252.68 | Yes | 15% | 252.68 | 219.7217 | Yes | No | Imported from Material!A85:F85 | Plumbing
MAT-0077 | 2026-05-28 | Original Material | Actual | Material | Finishing | Finishing | All Units | Tile cutting tool |  | 15 |  |  | 87.28 | Yes | 15% | 87.28 | 75.8957 | Yes | No | Imported from Material!A86:F86 | Finishing
MAT-0078 | 2026-05-29 | Original Material | Actual | Material | Rough | Rough | All Units | Misc |  | 15 |  |  | 96.01 | Yes | 15% | 96.01 | 83.487 | Yes | No | Imported from Material!A87:F87 | Rough
MAT-0079 | 2026-06-02 | Original Material | Actual | Material | Finishing | Finishing | All Units | Kitchen carpentry tools |  | 15 |  |  | 22.97 | Yes | 15% | 22.97 | 19.9739 | Yes | No | Imported from Material!A88:F88 | Finishing
MAT-0080 | 2026-06-07 | Original Material | Actual | Material | Plumbing | Plumbing | All Units | Kitchen Faucets | Amazon | 15 |  |  | 862.2 | Yes | 15% | 862.2 | 749.7391 | Yes | No | Imported from Material!A89:F89 | Plumbing Finishing
MAT-0081 | 2026-06-07 | Original Material | Actual | Material | Finishing | Finishing | All Units | Mirrors | Costway | 15 |  |  | 1163.65 | Yes | 15% | 1163.65 | 1011.8696 | Yes | No | Imported from Material!A90:F90 | Finishing
MAT-0082 | 2026-06-08 | Original Material | Actual | Material | Finishing | Finishing | All Units | Closet rack end caps | RONA | 15 |  |  | 30.18 | Yes | 15% | 30.18 | 26.2435 | Yes | No | Imported from Material!A91:F91 | Finishing
MAT-0083 | 2026-06-10 | Original Material | Actual | Material | Painting | Painting | All Units | Benjamin Moore Paint |  | 15 |  |  | 245.99 | Yes | 15% | 245.99 | 213.9043 | Yes | No | Imported from Material!A92:F92 | Painting
MAT-0084 | 2026-06-12 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | Home Depot | 15 |  |  | 821.06 | Yes | 15% | 821.06 | 713.9652 | Yes | No | Imported from Material!A93:F93 | General conditions
MAT-0085 | 2026-06-12 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | Home Depot | 15 |  |  | 112.08 | Yes | 15% | 112.08 | 97.4609 | Yes | No | Imported from Material!A94:F94 | General conditions
MAT-0086 | 2026-06-12 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | Home Depot | 15 |  |  | 140.14 | Yes | 15% | 140.14 | 121.8609 | Yes | No | Imported from Material!A95:F95 | General conditions
MAT-0087 | 2026-06-12 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | RONA | 15 |  |  | 282.83 | Yes | 15% | 282.83 | 245.9391 | Yes | No | Imported from Material!A96:F96 | General conditions
MAT-0088 | 2026-06-13 | Original Material | Actual | Material | General Conditions | General Conditions | All Units | Misc | Home Depot | 15 |  |  | 267.67 | Yes | 15% | 267.67 | 232.7565 | Yes | No | Imported from Material!A97:F97 | General conditions
MAT-0089 | 2026-06-15 | Original Material | Actual | Material | Finishing | Finishing | All Units | Blank Wall Plates | Amazon | 15 |  |  | 242.06 | Yes | 15% | 242.06 | 210.487 | Yes | No | Imported from Material!A98:F98 | Finishing
MAT-0090 | 2026-06-29 | Original Material | Actual | Material | Finishing | Finishing | All Units | Kitchen Handles | Amazon | 15 |  |  | 635.89 | Yes | 15% | 635.89 | 552.9478 | Yes | No | Imported from Material!A99:F99 | Finishing
LAB-0001 |  | Original Actual Labor | Actual | Labour | Demo | Demo | All Units | Demo | Ben | 15 |  |  | 4393.77 | Yes | 15% | 4393.77 | 3820.6696 | Yes | No | Imported from Material!P11:U11
LAB-0002 |  | Original Actual Labor | Actual | Labour | Demo | Demo | All Units | Demo | ben | 15 |  |  | 2434 | Yes | 15% | 2434 | 2116.5217 | Yes | No | Imported from Material!P12:U12
LAB-0003 |  | Original Actual Labor | Actual | Labour | Demo | Demo | All Units | Demo | Prediction Raul | 15 |  |  | 4000 | Yes | 15% | 4000 | 3478.2609 | Yes | No | Imported from Material!P13:U13
LAB-0004 |  | Original Actual Labor | Actual | Labour | OHP | OHP | All Units | ohp | arya | 15 |  |  | 2650 | Yes | 15% | 2650 | 2304.3478 | Yes | No | Imported from Material!P14:U14
LAB-0005 |  | Original Actual Labor | Actual | Labour | Labour | General Labour | All Units | General Labor | jair | 15 |  |  | 70000 | Yes | 15% | 70000 | 60869.5652 | Yes | No | Imported from Material!P15:U15
LAB-0006 |  | Original Actual Labor | Actual | Labour | Kitchen | Kitchen | All Units | Kitchen building | Lucas | 15 |  |  | 3250.67 | Yes | 15% | 3250.67 | 2826.6696 | Yes | No | Imported from Material!P16:U16
LAB-0007 |  | Original Actual Labor | Actual | Labour | Labour | Labour | All Units | Water main burst | Mike | 15 |  |  |  | Yes | 15% | 0 | 0 | No | No | Imported from Material!P17:U17
LAB-0008 |  | Original Actual Labor | Actual | Labour | Kitchen | Kitchen | All Units | Kitchen dishwasher mod | Lucas Suda | 15 |  |  |  | Yes | 15% | 0 | 0 | No | No | Imported from Material!P18:U18
LAB-0009 |  | Original Actual Labor | Actual | Labour | Kitchen | Kitchen | All Units | Kitchen install extra | Wan | 15 |  |  |  | Yes | 15% | 0 | 0 | No | No | Imported from Material!P19:U19

## Scope_Budget
Scope Budget / Allowances / Quotes
Per-unit constants, quotes, allowances, and manually approved totals belong here. This replaces formulas that used neighbouring labels or row-position multipliers.
Line_ID | Line_Role | Source_Type | Cost_Class | Trade | Cost_Code | Scope_Area | Item | Unit_Price | Quantity_Per_Affected_Unit | Affected_Units | Manual_Total_Incl_Tax | Tax_Included | Tax_Rate | Amount_Incl_Tax | Amount_Excl_Tax | Include_Current_Forecast | Include_Quote_Total | Include_Target_Budget | Notes
ALLOW-0001 | Allowance | Current_Forecast | Material | Plumbing | Bathroom/Plumbing | All Units | Plumbing fixtures/finishings per unit | 2150 | 1 | 15 |  | Yes | 15% | 32250 | 28043.4783 | Yes | No | No | Original Material!I5. Replaces manual '+I5*15' formula logic.
ALLOW-0002 | Allowance | Current_Forecast | Material | Kitchen | Kitchen | All Units | Cabinets | 2200 | 1 | 15 |  | Yes | 15% | 33000 | 28695.6522 | Yes | No | No | Original Material!I6.
ALLOW-0003 | Allowance | Current_Forecast | Material | Kitchen | Kitchen | All Units | Counter per unit | 900 | 1 | 15 |  | Yes | 15% | 13500 | 11739.1304 | Yes | No | No | Original Material!I7.
QLAB-0001 | Quote_Line | Quote | Labour | Labour | General Labour | All Units | General Labour | 6800 | 1 | 15 |  | No | 15% | 102000 | 102000 | No | Yes | No | Quoted labour line from original Material tab.
QLAB-0002 | Quote_Line | Quote | Labour | Labour | Demo | All Units | Demolition/Waste disposal | 600 | 1 | 15 |  | No | 15% | 9000 | 9000 | No | Yes | No | Quoted labour line from original Material tab.
QLAB-0003 | Quote_Line | Quote | Labour | Labour | Cleaning | All Units | Cleaning | 200 | 1 | 15 |  | No | 15% | 3000 | 3000 | No | Yes | No | Quoted labour line from original Material tab.
QLAB-0004 | Quote_Line | Quote | Labour | Labour | General Conditions | All Units | Superintendant + Material Delivery | 200 | 1 | 15 |  | No | 15% | 3000 | 3000 | No | Yes | No | Quoted labour line from original Material tab.
QMATD-0001 | Quote_Detail | Quote | Material | Material | Material Quote Detail | All Units | Tile Trim | 0 | 4 | 1 |  | No | 15% | 0 | 0 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0002 | Quote_Detail | Quote | Material | Material | Rough | All Units | Self leveling | 0 | 4 | 1 |  | No | 15% | 0 | 0 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0003 | Quote_Detail | Quote | Material | Material | Rough | All Units | Drywall | 36 | 4 | 1 |  | No | 15% | 144 | 144 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0004 | Quote_Detail | Quote | Material | Material | Material Quote Detail | All Units | Joint Compound | 0 | 4 | 1 |  | No | 15% | 0 | 0 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0005 | Quote_Detail | Quote | Material | Material | Painting | All Units | Paint | 30 | 6 | 1 |  | No | 15% | 180 | 180 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0006 | Quote_Detail | Quote | Material | Material | Material Quote Detail | All Units | Caulking + Silicone | 15 | 3 | 1 |  | No | 15% | 45 | 45 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0007 | Quote_Detail | Quote | Material | Material | Material Quote Detail | All Units | Sills | 42 | 2 | 1 |  | No | 15% | 84 | 84 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0008 | Quote_Detail | Quote | Material | Material | Bathroom/Plumbing | All Units | Bathroom + Kitchen finishing | 1850 | 1 | 1 |  | No | 15% | 1850 | 1850 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0009 | Quote_Detail | Quote | Material | Material | Kitchen | All Units | Kitchen | 2000 | 1 | 1 |  | No | 15% | 2000 | 2000 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0010 | Quote_Detail | Quote | Material | Material | Kitchen | All Units | counter | 800 | 1 | 1 |  | No | 15% | 800 | 800 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0011 | Quote_Detail | Quote | Material | Material | Bathroom/Plumbing | All Units | Plumbing rough material | 300 | 1 | 1 |  | No | 15% | 300 | 300 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMATD-0012 | Quote_Detail | Quote | Material | Material | Electrical | All Units | Electrical rough material | 200 | 1 | 1 |  | No | 15% | 200 | 200 | No | No | No | Detail line from original quoted material table. Not included in quote total because original also had a manual total override.
QMAT-OVERRIDE | Quote_Total_Override | Quote | Material | Material | Material Quote | All Units | Quoted Material Total Override |  |  |  | 20593.73 | No | 15% | 20593.73 | 20593.73 | No | Yes | No | Original Material!S53 hardcoded total. Use this as quote total unless replaced by detailed rows.

## Change_Orders
Change Orders / Extras
Billable and Include_In_Progress are explicit flags. Totals do not infer inclusion from Status text.
CO_ID | Item | Description | Cost_Per_Unit | Applied_Units | Total_Before_OHP | Status | Billable | Include_In_Progress | OHP_Rate | Total_With_OHP | Reason | Original_Source
CO 1 | Kitchen Cabinets | Change Standard 12" Upper Cabinets to 15" | 600 | 15 | 9000 | Cancelled | No | No | 15% | 0 | Not charged: Canceled | EXTRAS!B5:I5
CO 2 | Curtains | Supply and install Curtains in all units | 600 | 10 | 6000 | Paid | Yes | Yes | 15% | 6900 | Not included in initial scope | EXTRAS!B6:I6
CO 3 | Dining Counter | Supply and install dining counter | 546 | 8 | 4368 | Not Executed | Yes | Yes | 15% | 5023.2 | Quartz countertop not included in initial scope | EXTRAS!B7:I7
CO 4 | Bathroom Doors | Enlarge Bathroom doors to 28" | 263.33 | 6 | 1579.98 | Paid | Yes | Yes | 15% | 1816.977 | Initial scope did not include enlarging 24" doors to 28" | EXTRAS!B8:I8
CO 5 | Closet Doors | Supply new closet doors and frames | 349.3333 | 15 | 5240 | Paid | Yes | Yes | 15% | 6026 | Original showed Cost/Unit 436.67, Applied Units 15, Total 5,240.00. Normalized Cost_Per_Unit to 5,240/15 so formula-driven table preserves the original total. | EXTRAS!B9:I9
CO 6 | Bathroom Doors | Supply new bathroom doors and frames | 436 | 6 | 2616 | Cancelled | No | No | 15% | 0 | Not charged: Included in initial scope | EXTRAS!B10:I10
CO 7 | Additional Walls | Raise Kitchen wall to ceilling for HVAC | 230 | 5 | 1150 | Paid | Yes | Yes | 15% | 1322.5 | Required for concealed HVAC pipes, requested by client | EXTRAS!B11:I11
CO 8 | HVAC Electrical | bring wires left by HVAC to pannel | 200 | 7 | 1400 | Paid | Yes | Yes | 15% | 1610 | HVAC installer left wires to be fished by our tem to pannel | EXTRAS!B12:I12
CO 9 | White wash brick | Paint, labor (taping), tool rental | 500 | 10 | 5000 | Not Executed | Yes | Yes | 15% | 5750 | Not included in initial scope | EXTRAS!B13:I13
CO 10 | Kitchen changes | Additions (dishwasher panel, side paneling, ect) | 250 | 15 | 3750 | Paid | Yes | Yes | 15% | 4312.5 | Changes to intitially quoted design | EXTRAS!B14:I14

## Order_Quantities
Order Quantities
Use Manual_Total_Units_Override only when pack math does not match the real ordering requirement. Otherwise Total_Units = Qty_Per_Pack × Number_Of_Packs.
Order_ID | Cost_Class | Cost_Code | Item | Qty_Per_Pack | Number_Of_Packs | Manual_Total_Units_Override | Total_Units | Order_Status | Notes
ORD-0001 | Material | Unassigned | SL-JIJI Bathroom Exhaust Fan Cover 12x12" (White) | 1 | 15 |  | 15 | Open
ORD-0002 | Material | Unassigned | Door Stoppers Chrome Cylindrical Floor Doorstops 2.5" | 4 | 3 |  | 12 | Open
ORD-0003 | Material | Unassigned | Aluminum Floor Transition Strip T Molding Silver 8.8ft | 3 | 5 |  | 15 | Open
ORD-0004 | Material | Unassigned | PMMASTO Coat Rack Wall Mount T-Hooks Polished Silver (2-pack) | 2 | 8 |  | 16 | Open
ORD-0005 | Material | Unassigned | Peasur 11.4" LED Ceiling Light Flush Mount 24W 6-Pack (White) | 6 | 8 |  | 48 | Open
ORD-0006 | Material | Unassigned | 5-Piece Polished Chrome Bathroom Hardware Accessories Set | 1 | 13 |  | 13 | Open
ORD-0007 | Material | Unassigned | LEDIARY 16-Pack LED Recessed Lighting 4" Slim Pot Light | 48 | 1 |  | 48 | Open
ORD-0008 | Material | Unassigned | MLLIZH 1-Gang Screwless Wall Plates Blank White (4-Pack) | 4 | 1 |  | 4 | Open
ORD-0009 | Material | Unassigned | Stelpro Uniwatt Non-Programmable Thermostat White UT202NP | 1 | 30 |  | 30 | Open
ORD-0010 | Material | Unassigned | BESTTEN 3-Gang Screwless Wall Plate Matte White (5-Pack) | 5 | 1 |  | 5 | Open
ORD-0011 | Material | Unassigned | Peasur 7" LED Ceiling Light Flush Mount 6-Pack (White) | 6 | 8 |  | 48 | Open
ORD-0012 | Material | Unassigned | Leviton Decora 15A Tamper-Resistant Duplex Receptacle (10-Pack) | 10 | 11 |  | 110 | Open
ORD-0013 | Material | Unassigned | BESTTEN 1-Gang Screwless Wall Plate Snow White (50-Pack) | 50 | 2 |  | 100 | Open
ORD-0014 | Material | Unassigned | Leviton Decora Single-Pole Switch 15A (10-Pack) | 10 | 9 |  | 90 | Open
ORD-0015 | Material | Unassigned | BESTTEN 2-Gang Screwless Wall Plate Snow White (10-Pack) | 10 | 7 |  | 70 | Open
ORD-0016 | Material | Unassigned | Leviton GFCI 15A Non-Tamper Receptacle (2-Pack) | 2 | 8 |  | 16 | Open
ORD-0017 | Material | Unassigned | ClosetMaid White Vinyl Coated Steel 6-ft L x 12-in | 1 | 13 |  | 13 | Open
ORD-0018 | Material | Unassigned | Door Stoppers Silver Cylindrical Floor Doorstops 2.4" | 10 | 2 |  | 20 | Open
ORD-0019 | Material | Unassigned | TG Screwless Blank Wall Plate, Child Safe Blank Device Outlet Cover | 5 | 2 |  | 10 | Open

## Cost_Code_Summary
Cost Code Summary — tag-based totals
This is the replacement for manually summing scattered C-column cells. Totals are SUMIFS by Cost_Code and flags, so sorting/appending input tables does not move totals.
Cost_Code | Primary_Class | Actual_Incl_Tax | Actual_Excl_Tax | Forecast_Addons_Incl_Tax | Forecast_Total_Incl_Tax | Quote_Incl_Tax | Billable_CO_Incl_Tax | Variance_vs_Forecast | Notes
Rough | Material | 33881.72 | 29462.3652 | 0 | 33881.72 | 0 | 0 | -33881.72
Finishing | Material | 43847.51 | 38128.2696 | 0 | 43847.51 | 0 | 0 | -43847.51
Bathroom/Plumbing | Material | 952.6 | 828.3478 | 32250 | 33202.6 | 0 | 0 | -33202.6 | Includes bathroom and plumbing entries.
Kitchen | Mixed | 3250.67 | 2826.6696 | 46500 | 49750.67 | 0 | 0 | -49750.67 | Cabinets/counters allowances plus kitchen labour/material.
Doors | Mixed | 14229.78 | 12373.7217 | 0 | 14229.78 | 0 | 0 | -14229.78 | Original workbook had a bad doors material formula. This row only sums Cost_Code = Doors.
Electrical | Material | 601.41 | 522.9652 | 0 | 601.41 | 0 | 0 | -601.41
HVAC | Material | 393.78 | 342.4174 | 0 | 393.78 | 0 | 0 | -393.78
Demo | Labour | 10827.77 | 9415.4522 | 0 | 10827.77 | 9000 | 0 | -1827.77
Painting | Material | 245.99 | 213.9043 | 0 | 245.99 | 0 | 0 | -245.99
General Conditions | Mixed | 1659.24 | 1442.8174 | 0 | 1659.24 | 3000 | 0 | 1340.76
General Labour | Labour | 70000 | 60869.5652 | 0 | 70000 | 102000 | 0 | 32000
OHP | OHP | 4720 | 4104.3478 | 0 | 4720 | 0 | 0 | -4720
Cleaning | Labour | 0 | 0 | 0 | 0 | 3000 | 0 | 3000
Material Quote | Material | 0 | 0 | 0 | 0 | 20593.73 | 0 | 20593.73 | Manual quoted material override.
Unassigned | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Use only temporarily; retag before reporting.

## Progress_Valuation
Progress Valuation
Progress/payment math is driven by settings and change-order flags. Completion percentages are explicit inputs.
Payment / Value Summary | Formula Result | Rule | Subject | Units | Completion_Pct | Unit_Price_PreTax | Quoted_After_Tax | Needed_To_Balance | Value_Completed
Current Payments To Date | 137969 | Project_Setup variable | 15 Units | 15 | 51% | 20580 | 355005 | 54913.95 | 209058.6645
Base Contract Total After Tax | 355005 | Base_Price_Per_Unit_PreTax × Total_Units × (1 + Tax_Rate) | Initial 10 Units | 10 | 68% | 20580 | 236670 | 36609.3 | 185829.924
Owes Before Extras | 217036 | Base Contract Total After Tax - Current Payments | 5 Additional Units | 5 | 21% | 20580 | 118335 | 18304.65 | 28694.3265
Billable Extras Before OHP | 28487.98 | Change_Orders Billable=Yes
Remainder of Project Cost | 245523.98 | Owes Before Extras + Billable Extras Before OHP
Billable Extras With OHP | 32761.177 | Change_Orders Billable=Yes with OHP | Actual Value | 409918.95
|  |  | Extras with OHP | 32761.177
|  |  | Received | -137969
|  |  | Total Remaining To Complete | 304711.127

## Lists
Cost_Class
Material | Actual | Yes | Yes | Rough | Paid | Allowance | Open
Labour | Forecast | No | No | Finishing | Not Executed | Quote_Line | Ordered
Subcontractor | Committed |  |  | Bathroom/Plumbing | Cancelled | Quote_Detail | Received
Equipment | Quote |  |  | Kitchen | Pending | Quote_Total_Override | Cancelled
General Conditions | Budget |  |  | Doors | Approved | Budget_Line | Backordered
OHP | Allowance |  |  | Electrical | Rejected | Forecast_Line
Other |  |  |  | HVAC
Demo
Painting
General Conditions
General Labour
OHP
Cleaning
Material Quote
Unassigned

## Parser_Contract
Parser Contract / Rules of Engagement
Object | Name | Range / Table | Primary Key | Parser Instruction | Formula Logic | Append/Sort Safe?
Workbook | Project_Setup | tblProjectSettings | Code | Read controlled variables by Code, not cell labels. | Constants feed formulas through SUMIFS lookups. | Do not sort unless formulas use Code lookups; table itself is safe.
Table | Cost_Ledger | tblCostLedger | Entry_ID | Canonical ledger for actual costs. Do not parse old visual sections. | Amount_Incl_Tax and Amount_Excl_Tax are calculated columns; summaries SUMIFS by Cost_Class/Cost_Code flags. | Yes
Table | Scope_Budget | tblScopeBudget | Line_ID | Canonical table for per-unit constants, allowances, quote rows, manual overrides. | Amount = manual total OR unit price × qty × affected units. Inclusion flags control summaries. | Yes
Table | Change_Orders | tblChangeOrders | CO_ID | Canonical extras/change order table. | Total = Cost_Per_Unit × Applied_Units; billable totals use Billable flag and OHP_Rate. | Yes
Table | Order_Quantities | tblOrderQuantities | Order_ID | Purchase quantity table. | Total_Units = override OR Qty_Per_Pack × Number_Of_Packs. | Yes
Summary | Dashboard | A3:D23 | Metric | Read results by Metric labels or formulas, not by coordinates if possible. | Top-level validation of original workbook values and new dynamic totals. | N/A
Summary | Cost_Code_Summary | tblCostCodeSummary | Cost_Code | Use this as the parser-facing replacement for scattered SUM formulas. | SUMIFS against canonical tables by Cost_Code and inclusion flags. | Yes
Rule | Never row-position sum | N/A | N/A | Reject formulas like SUM(C6:C69) when they intend a trade/category total. | Use SUMIFS(tblCostLedger[Amount],tblCostLedger[Cost_Code],target). | N/A
Rule | Explicit inclusions | N/A | N/A | Status text is not enough. Use Include_In_Actual, Include_Current_Forecast, Include_Quote_Total, Billable. | Flags are the source of truth. | N/A
Rule | Per-unit math | N/A | N/A | Never encode multipliers in label text like '15 units'. | Use Affected_Units or Project_Setup Total_Units. | N/A
Imported anomaly | Original Doors material | Material!J36 | N/A | Original formula labelled Doors summed C6:C69, effectively most material spending. | Template fixes this: Doors only means Cost_Code=Doors. | N/A