## Sheet1
Design Phase | Task | Notes | Sub-tasks
SD | Project Kick off + Goals |  | -Prepare Timeline Documents -Allocation Resources -Identify client goals, program requirements, sustainability goals -Establish file sharing and issue tracking ptotocols -Clarify delivery method (Design-build/ IPD/ CMGC/ etc)
SD | Site Analysis + Constaints |  | -Conduct site study (solar orientation, access, zoning, topography) -Consider craning zones, trucking access, staging areas, etc
SD | Define Energy Performance Criterea |  | -Energy and carbon targets (EUI, airtightness, embodies carbon) -Engage energy consultants -Align with certification pathways (PHIUS, LEED, PassivHaus)
SD | Conceptual Design Development |  | -Generate massing/ layout options, structural spans -Prioritize thermal continuity, airtightness, service routing in conceptual plans
SD | Prelim. Massing + Energy Modeling |  | -Conduct early whole-building energy model and solar studies -Develop 3D model of building envelope and surrounding buildings -Development of default dataset for window U-values, assembly R-values, ventilation, HVAC, appliances -Development of different costing options with different design explorations
SD | Establish Structural + Envelope Strategy |  | -Explore primary structure -Explore offsite enclosure and structural manufacturer candidates -Select structural engineer -Select MEP engineer -Explore GC candidates
SD | Preliminary Cost + Feasability Review |  | - Rough Order of Magnitude, prepare early factory Request For Proposals (collab with estimator/ builder to validate budget and factor in off-site savings vs logistics and coordination costs)
SD | Engage Structural Engineer
SD | Engage MEP Engineer
SD | Coordinate Building Systems Strategy |  | -Discuss HVAC, plumbing, electrical approaches, -Discuss systems vs pre-fab elements
SD | Preliminary Code + Zoning Check |  | -Perform zoning analysis and code scan (fire rating, egress, heights/ area, building use/ occupancy type) -Review implications of modular/ offsite elements for inspections/ approvals
SD | 3D Massing + System Visualization |  | -Early 3D models that show (structural logic + panel strategy). Essentially update model to DfMA logic
SD | Preliminary Fabricator Coordination |  | -Share conceptual layouts with potential fabricators -Confirm preffered panel sizes, tolerences, material limits, handling constraints -Confirm factory supply only vs supply (and install mileage radiuses)
SD | SD Review + Client Sign-Off | SD Package includes: -Plans, Sections, Elevations -3D views -Energy/ comfort targets -Offsite strategy (prelim) -System diagrams (prelim) | -Present SD package -Obtain client and consultant alignment before advancing to DD
SD | Updated Energy Modeling + Certification Submissions |  | -Window options to be modeled, accurate shading factors, updated 3D model, updated takeoff documents, assemblies need to be modeled, semi-conditioned spaces need to be identified and calculated, possible thermal bridges need to be identified and calculated, strategy for ventilation, HVAC, appliances, MEL loads, additional energy loads, energy use calculations.
DD | Develop Envelope Assembly Details |  | -Define wall, floor, roof assemblies based on performance and fabrication inputs -Coordinate thermal, vapour, airtightness layers (WRB, insulation, membranes, taping strategy, flashing etc) -Detail transitions between factory-installed and site-installed components (foundation-to-wall, roof-to-wall, etc.) -Architects details checklist (verify with Sean)
DD | Refine Building Geometry + Layouts |  | -Lock in massing, structural grid, assembly zoning -Finalize room size, wall alignments, core locations to align with panel logics -Optimize layouts for minimal thermal bridging and mechanical distribution
DD | Confirm Structural Strategy |  | -Coordinate with structural engineer and fabricator to finalize: -Primary structure, panel size limits and connections, lifting, handling, erection constraints
DD | MEP Coordination with Off-Site Elements |  | -Define MEP routing strategy (horizontal/ vertical stacks, dropped ceilings, core zones) -Identify factory-prepped MEP penetrations or pre-installed components -Align duct and plumbing paths with panel seams, stacks, raceways
DD | Update Energy Model + Building Performance Metrics |  | -Refine model based on material properties and form -Coordinate with energy consultants for updates to: -Heating/ cooling loads, EUI/ PassivHaus compliance, Component U-values and airtightness assumptions
DD | Confirm Window and Door Package |  | -Select window types, performance specs (U-value, SHGC, air infiltration) -Align window installation details with panel strategy (in-factory vs site-set) -Confirm buck detailing, shading elements, sill/ jamb/ head continuity
DD | Develop Panelization + Assembly Strategy |  | -Create detailed panel layouts (plan + elevation) -Define logical assembly zones (panel joints at party walls, floor breaks, etc) -Coordinate air/ water continuity across panel seams -Begin production of system interface drawings and zone-based diagrams
DD | Material Selections + Finish Systems |  | -Confirm major exterior materials (siding/ cladding systems/ WRB compatibility/ fastener strategy) -Select interior assemblies (GWB, acoustics, vapour control) -Ensure compatibility with panel shop process (fire ratings, vapour drive, drying potential)
DD | Code Compliance + Detailing | Compliance Documentation | -Advance egress, accessibility, and fire-rated assemblies -Confirm panel fire resistance, joint conditions, floor-to-floor separation -Prepare compliance documentation for review with AHJ (authorities having jurisdiction)
DD | Digital Model Coordination |  | -Organize model by subgroups for fabrication and assembly review -Set up views for coordination (screenshots or saved views) -Begin data-layer orientation (for BIM)
DD | Fabricator + Consultant Review |  | -Share DD drawing set and digital model with: -Enclosure panel providor, timber fabricator, MEP engineer for clash detection -Incorporate feedback on tolerances, installation steps, pre-assembly options
DD | Cost Estimate + Schedule Alignment |  | -Update construction cost estimate based on DD set -Refine panel count, material use, logistics assumptions -Identify early procurement needs for long-lead items (windows, membranes, etc)
DD | Client Presentation + Sign Off | DD Package includes: -Floor plans, elevations, building sections -Wall/ roof assemblies -Panel diagrams, perforamance strategy -Updated 3D visuals and zone-based construction strategy | -Present updated DD drawing set -Secure client and team alignment before proceeding to CD and fabrication detailing
CD | Finalize Integrated Drawings for Permit + Construction |  | -Develop comprehensive architectural drawing set with: Fully dimensioned floor plans, RCPs, and finish plans, Building elevations with material callouts, Building sections showing assemblies and floor transitions. -Include phasing or assembly diagrams if required by AHJ for modular/ off-site scopes
CD | Detail All Building Assemblies |  | -Finalize high performance assemblies (wall, roof, floors) with: Airtightness and WRB continuity, Insulation layers with R-values and materials, Fire ratings and acoustic separations, Expansion joints, tolerances, air/vapour control layers
CD | Develop High-Resolution Building Sections + Enlarged Details |  | -Provide key section cuts through: Foundation-to-wall and wall-to-roof, Window and door interfaces (all typical conditions) Panel seams and service penetrations
CD | Coordinate Fully With Structural + MEP Disciplines |  | -Integrate final structure with panel layout and load paths -Overlay MEP systems in: Dropped ceilings, shafts, panel cavities Mechanical rooms or pods
CD | Finalize Window and Door Details |  | -Provide detailed installation drawings (bucks, anchors, air-sealing, sill drainage) -Indicate which units are factory installed vs-site-installed -Coordinate opening tolerances with panel fabricator -Coordinate all typical exterior door threshold details -Provide min. 3/4" scale window-to-wall sections to include: Interior wall finishes at openings, Exterior wall finishes at openings
CD | Prepare Full Schedules + Specifications |  | -Door/ window schedules with tags matching plans and elevations -Room finish schedule, material keynotes, equipment locations -Specifications that include: Performance targets (airtightness, U-value, acoustic), Work scopes for panel fabricator vs site team Mock-up and testing requirements (blower door, water infiltration, thermal scan)
CD | Clash Coordination + Digital Checks |  | -Run final clash detection test in BIM model: Structural elements with MEP panels, Service penetrations vs panel seams and joints -Tag areas requiring builder or fabricator coordination (dense assemblies, interstitial zones, etc.)
CD | Issue Permit + Construction Sets | CD Package includes: -Coordinated PDFs -3D models (or views/ screenshots) -Indexed assembly callouts and flagged zones | -Create a permit-ready set with: Jurisdiction-specific code notes and energy compliance documentation -Prepare a fabricator-ready CD set
CD | CD-Level Client and Consultant Review |  | -Present final CD set for review and sign-off: Confirm scope boundaries (factory-built vs site-built) Review assembly sequencing strategy Clarify construction tolerances and QA responsibilities
CD | Support Fabrication Model Development |  | -Provide reference drawings and model data for fabrication details
CD | Support Preconstruction Planning |  | -Assist GC and trades in: Logistics planning, Temporary protection of factory-installed elements Site prep requirements (dimensional tolerance, substrate compatibility) -Provide updated DfMA, fabrication, site readiness, installation schedule and responsibilities DOC)
CA | Submittal Review (as needed) |  | -Review final shop drawings, hardware schedules, and submittals provided by fabricators -Confirm alignment with fabricator-approved design -Provide fast turnaround responses to reduce factory downtime
CA | Installation Observation (support, not supervision) |  | -Perform site visits during panel installation if requested -Confirm that installed assemblies match design intent, especially: Window and door placement Panel-to-panel alignment Key air barrier, WRB, insulation transitions
CA | Clarification Requests |  | -Respond to occasional RFIs or clarifications from GC or factory -Use screenshots, markups, or online viewer as needed for fast communication
CA | Punch List Coordination
CA | Close-Out Documentation (if required)